## Project Summary
Project Summary (read-only)
Project Name | 1319D GMD ACS Client
Project Manager | ethan_lin@pesi.com.tw
Start date | 2024-07-17
Finish date | 2024-10-18
Days | Pro
Progress | 55.73%
Work hours | Pro
Remaining work hours | Pro
Remaining work days | Pro
Remaining weeks | Pro
Cost | Pro

## Task Schedule
[8 empty] | July 2024 | [23 empty] | August 2024 | [30 empty] | September 2024 | [29 empty] | October 2024
WBS | Task description | Start date | Finish date | 實際完成時間 | Progress | Owner | Note | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6
wbs | task | start | finish |  | progress |  |  | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | # | #
¦
1 | 基本架構 | 2024-07-17 | 2024-07-18 | 2024-07-18 | 100% | [11 empty] | = | = | [41 empty] | ¦
¦
2 | RESTful | 2024-07-19 | 2024-10-18 |  | 83.51% | [13 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
2.1 | provision 服務開通 | 2024-07-19 | 2024-10-04 |  | 92.26% | [13 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
2.1.1 | Send command to Server | 2024-07-19 | 2024-07-19 | 2024-07-18 | 100% |  | 取得eth mac需要misc service 目前使用tgateway樣機資訊才能連上 | [11 empty] | = | [40 empty] | ¦
2.1.2 | Handle server callback data | 2024-07-19 | 2024-10-04 |  | 92% | [13 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
2.1.2.1 | parse data | 2024-07-19 | 2024-07-19 | 2024-07-22 | 100% | [13 empty] | = | [40 empty] | ¦
2.1.2.2 | process data | 2024-07-22 | 2024-10-04 |  | 91.72% | [16 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
2.1.2.2.1 | 文件或實際data已知部分 | 2024-07-22 | 2024-08-07 | 2024-08-13 | 100% | [16 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | [21 empty] | ¦
2.1.2.2.2 | 不知道怎麼做，提問fii部分 | 2024-09-23 | 2024-10-04 |  | 80% |  | http doc和實際data欄位比較 provision 紅色跟橘色部分 | [52 empty] | ¦ | [24 empty] | = | = | = | = | = | = | = | = | = | =
2.2 | fwinfo fw 檢查及更新 | 2024-07-24 | 2024-10-09 |  | 57.14% | [18 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
2.2.1 | Send command to Server | 2024-07-24 | 2024-07-24 | 2024-07-23 | 100% | [18 empty] | = | [35 empty] | ¦
2.2.2 | Handle server callback data | 2024-08-07 | 2024-08-09 |  | 100% | [32 empty] | = | = | = | [19 empty] | ¦
2.2.2.1 | parse data | 2024-08-07 | 2024-08-07 | 2024-08-13 | 100% | [32 empty] | = | [21 empty] | ¦
2.2.2.2 | process data | 2024-08-08 | 2024-08-09 | 2024-08-19 | 100% |  | system mode 可以在下載完更新檔後 a. 立即更新 b.在待機狀態時更新c 在下次重開機後更新 d.在指定時間段更新(e. 01:00~05:00) user mode 會跳出通知提醒用戶主動更新 PESI指定時段設計為時段內每30分鐘送出一次OTA | [31 empty] | = | = | [19 empty] | ¦
2.2.3 | OTA UPDATER APK修改/測試 | 2024-10-07 | 2024-10-09 |  | 0% |  | 見 送到其他APK分頁 | [52 empty] | ¦
2.3 | appinfo app 安裝 更新及移除 | 2024-07-29 | 2024-10-15 |  | 66.67% | [23 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | =
2.3.1 | Send command to Server | 2024-07-29 | 2024-07-29 | 2024-07-23 | 100% | [23 empty] | = | [30 empty] | ¦
2.3.2 | Handle server callback data | 2024-08-12 | 2024-08-14 |  | 100% | [37 empty] | = | = | = | [14 empty] | ¦
2.3.2.1 | parse data | 2024-08-12 | 2024-08-12 | 2024-08-20 | 100% | [37 empty] | = | [16 empty] | ¦
2.3.2.2 | process data | 2024-08-13 | 2024-08-14 | 2024-08-21 | 100% | [38 empty] | = | = | [14 empty] | ¦
2.3.3 | APP DOWNLOAD MANAGER測試 | 2024-10-14 | 2024-10-15 |  | 0% | [54 empty] | ¦
2.4 | launcherinfo 更新Launcher 設定 | 2024-08-01 | 2024-08-20 |  | 100% | [26 empty] | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | = | [8 empty] | ¦
2.4.1 | Send command to Server | 2024-08-01 | 2024-08-01 | 2024-07-23 | 100% | [26 empty] | = | [27 empty] | ¦
2.4.2 | Handle server callback data | 2024-08-15 | 2024-08-20 |  | 100% | [40 empty] | = | = | = | = | = | = | [8 empty] | ¦
2.4.2.1 | parse data | 2024-08-15 | 2024-08-15 | 2024-08-29 | 100% | [40 empty] | = | [13 empty] | ¦
2.4.2.2 | process data | 2024-08-16 | 2024-08-20 | 2024-08-29 | 100% | [41 empty] | = | = | = | = | = | [8 empty] | ¦
2.5 | MISC service | 2024-10-16 | 2024-10-17 |  | 0% | [54 empty] | ¦
2.5.1 | get eth mac | 2024-10-16 | 2024-10-17 |  | 0% | 在X5M放到PRIV-APP就可以? | [53 empty] | ¦
2.6 | GET 廣告 | 2024-10-18 | 2024-10-18 | 2024-08-22 | 100% | [54 empty] | ¦
2.7 | GET 本周強檔 | 2024-10-18 | 2024-10-18 | 2024-08-22 | 100% | [54 empty] | ¦
2.8 | GET 排行榜 | 2024-10-18 | 2024-10-18 | 2024-08-22 | 100% | [54 empty] | ¦
2.9 | DATA PROVIDER | 2024-08-22 | 2024-08-22 | 2024-08-22 | 100% | [47 empty] | = | [6 empty] | ¦
2.10 | 關掉mqtt lib non-protected broadcast log |  |  |  | 0% | [54 empty] | ¦
2.11 | setting畫面的acs client apk要移除強制停止選項 |  |  |  | 0% | [54 empty] | ¦
¦
3 | MQTT | 2024-08-21 | 2024-09-20 |  | 0% | [54 empty] | ¦
3.1 | Server Command | 2024-08-21 | 2024-09-20 |  | 0% | [54 empty] | ¦
3.1.1 | reboot | 2024-08-21 | 2024-08-21 |  | 0% | [54 empty] | ¦
3.1.2 | getinfo | 2024-08-21 | 2024-08-23 |  | 0% | [54 empty] | ¦
3.1.3 | screencapture | 2024-08-26 | 2024-08-26 |  | 0% | [54 empty] | ¦
3.1.4 | btunpair | 2024-08-26 | 2024-08-26 |  | 0% | [54 empty] | ¦
3.1.5 | set_parental_lock | 2024-08-27 | 2024-08-28 |  | 0% | [54 empty] | ¦
3.1.6 | doFactoryReset | 2024-08-29 | 2024-08-29 |  | 0% | [54 empty] | ¦
3.1.7 | get_HDMI_Info | 2024-08-30 | 2024-09-03 |  | 0% | [54 empty] | ¦
3.1.8 | instantMonitoring | 2024-09-04 | 2024-09-06 |  | 0% | [54 empty] | ¦
3.1.9 | force_tune | 2024-09-09 | 2024-09-09 |  | 0% | [54 empty] | ¦
3.1.10 | channel_scan | 2024-09-09 | 2024-09-10 |  | 0% | [54 empty] | ¦
3.1.11 | open_browser | 2024-09-11 | 2024-09-12 |  | 0% | [54 empty] | ¦
3.1.12 | clear_auth |  |  |  | 0% | [54 empty] | ¦
3.1.13 | clear_provision |  |  |  | 0% | [54 empty] | ¦
3.1.14 | network_speed_test | 2024-09-13 | 2024-09-16 |  | 0% | [54 empty] | ¦
3.1.15 | signal_detect | 2024-09-17 | 2024-09-17 |  | 0% | [54 empty] | ¦
3.1.16 | pa_reset | 2024-09-18 | 2024-09-18 |  | 0% | [54 empty] | ¦
3.1.17 | status_update | 2024-09-19 | 2024-09-20 |  | 0% | [54 empty] | ¦
¦

## DB content provider
PROVIDER URL | content://com.prime.acsclient.prodiver/ACSData
PROVIDER實作的DB TABLE NAME | PESI_ACS_DATA_TABLE
PROVIDER實作的DB欄位名 | PROVIDER實作的DB欄位型態
_ID | integer
name | text not null unique
value | text

## 送到其他APK的broadcast
| 資料來源 | provider欄位 | 送到的package name | 送出的intent action | data provider內容 | 說明 | t.gw在launcher的相關字串
provision | provision | music_category | "com.prime.dmg.launcher" | "com.prime.acsclient.update.music_category" | [ {"name":"華語音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330858497.png", "sort":1, "servicelists":["1534", "1535", "1536", "1543"]}, {"name":"西洋音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330890167.png", "sort":2, "servicelists":["1514", "1515", "1516", "1517", "1518", "1519", "1521"]}, {"name":"東洋音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330824653.png", "sort":3, "servicelists":["1525", "1526", "1527"]}, {"name":"沙發音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330938131.png", "sort":4, "servicelists":["1522", "1523", "1524", "1528", "1531", "1532"]}, {"name":"古典音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330777070.png", "sort":5, "servicelists":["1529", "1530", "1537"]}, {"name":"其他音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586331013427.png", "sort":6, "servicelists":["1520", "1533", "1538", "1539", "1540", "1541", "1542"]}] | 音樂頻道分類 | "com.vasott.acsclient.update_music_category"
|  | Eula | "com.prime.dmg.launcher" | "com.prime.acsclient.update.Eula" | [{"name":"t.Gateway服務條款", "sort":1, "url":"https://www.tbc.net.tw/terms/tgatewaymemberservices", "version":"1.0.0"}] | t.Gateway服務條款
|  | IllegalNetwork | "com.prime.dmg.launcher" | "com.prime.acsclient.update.IllegalNetwork" | 0 |  | "com.vasott.acsclient.update_network_check"
|  | projectId | "com.prime.dmg.launcher" | "com.prime.acsclient.update.projectId" | 1 |  | PROPERTY_PROJECT_ID tbc ->1 dmg ->2 nkh -3
|  | networkQualityDefined | "com.prime.dmg.launcher" | "com.prime.acsclient.update.networkQualityDefined" | [ {"name":"EXCELLENT", "description":"優", "highest":1000, "lowest":30, "id":1}, {"name":"GOOD", "description":"好", "highest":30, "lowest":10, "id":2}, {"name":"MODERATE", "description":"普通", "highest":10, "lowest":1, "id":3}, {"name":"POOR", "description":"差", "highest":1, "lowest":0, "id":4}] | 測速結果顯示用 | t.gw的tvsettings找"network_quality_defined"
|  | launcher_profile | "com.prime.dmg.launcher" | "com.prime.acsclient.update.launcher_profile" | [ { "appName": "Prime Video(5.7.13+v14.0.0.397-armv7a)", "packageName": "com.amazon.amazonvideo.livingroom", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1659963445442.png", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "505007013", "apkLabel": "Prime Video", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "HBO GO(1.0.60)", "packageName": "com.hbo.asia.androidtv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1588849192037.png", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "1811261503", "apkLabel": "HBO GO", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "myVideo(4.0.0.11)", "packageName": "com.taiwanmobile.myVideotv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1648799080664.jpg", "iconPriority": 1, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "181", "apkLabel": "myVideo", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "Friday影音", "packageName": "net.fetnet.fetvod.tv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1582798646071.png", "iconPriority": 0, "activityName": "", "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "56", "apkLabel": "friDay影音", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "com.litv.cable.home(3.7.29-Cable)", "packageName": "com.litv.cable.home", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1600681975745.png", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "30729", "apkLabel": "com.litv.cable.home", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "MoveVTV(1.6)", "packageName": "com.hihealth.movevTv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1636453497296.png", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": null, "fullText": null, "appPath": "https://www.tbc.net.tw/media/MoveVTV1.6.apk", "appVersionCode": "8", "apkLabel": "MoveVTV", "screenCaptures": [], "displayPosition": 1, "forceUpdate": true }, { "appName": "國圖到你家(2.05)", "packageName": "tw.org.itri.nclibrary", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1645430183724.png", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "205", "apkLabel": "國圖到你家", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "CatchPlay", "packageName": "com.catchplay.asiaplay.common.tv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1582798799999.png", "iconPriority": 0, "activityName": "", "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "89", "apkLabel": "CATCHPLAY+", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "KKTV", "packageName": "com.kktv.kktv.tv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1590398011181.png", "iconPriority": 0, "activityName": "", "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "86", "apkLabel": "com.kktv.kktv.tv", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "三竹股市(1.87)", "packageName": "com.mitake.tv", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1699427028278.jpg", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "14", "apkLabel": "三竹股市", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false }, { "appName": "MABOW TV(v2.69.2)", "packageName": "tw.com.mabow.liveinteraction", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1599629663069.png", "iconPriority": 0, "activityName": null, "productId": "", "packageParams": {}, "description": "", "fullText": "", "appPath": "", "appVersionCode": "1422", "apkLabel": "MABOW TV", "screenCaptures": [], "displayPosition": 1, "forceUpdate": false } ], | 應用程式推薦 | LayoutConfigs
provision | DeviceOperation | TVMAILStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.TVMAILStatus" | 1 |  | tv_mail_status
|  | DVRStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.DVRStatus" | 0 |  | dvr_status
|  | DTVStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.DTVStatus" | 1
|  | IPWhitelistStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.IPWhitelistStatus" | 0 |  | "com.vasott.acsclient.ip_whitelist_status"
|  | TickerStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.TickerStatus" | 1 | 跑馬燈 | ticker_status
|  | SystemAlertStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.SystemAlertStatus" | 0 |  | "com.vasott.acsclient.system_alert_status"
|  | LauncherLockStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.LauncherLockStatus" | 0
|  | StandbyRedirectStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.StandbyRedirectStatus" | 1 |  | standby_redirect_status
|  | ForceScreenStatus | "com.prime.dmg.launcher" | "com.prime.acsclient.update.ForceScreenStatus" | 0 |  | "force_screen_status"
|  | pin_code | "com.prime.dmg.launcher" | "com.prime.acsclient.update.pin_code" | "0955098520" |  | "worker_password"
pa_day
|  | home_id | "com.prime.dmg.launcher" | "com.prime.acsclient.update.home_id" | "99999993"
|  | nit_id | "com.prime.dmg.launcher" | "com.prime.acsclient.update.nit_id" | "12" |  | "nit_id"
|  | zipcode | "com.prime.dmg.launcher" | "com.prime.acsclient.update.zipcode" | "320681" |  | "zipcode"
|  | so | "com.prime.dmg.launcher" | "com.prime.acsclient.update.so" | "1" |  | "so"
|  | bat_id | "com.prime.dmg.launcher" | "com.prime.acsclient.update.bat_id" | "0" |  | "bat_id"
|  | box_si_nit | "com.prime.dmg.launcher" | "com.prime.acsclient.update.box_si_nit" | "12" |  | "box_si_nit"
|  | network_sync_time | "com.prime.dmg.launcher" | "com.prime.acsclient.update.IllegalNetwork" | "360" |  | "com.vasott.acsclient.update_network_check"
| 其他資料 | ad_list | "com.prime.dmg.launcher" | "com.prime.acsclient.update.ad_list" | { "tvRecommendations": [ { "page": "1", "type": "Full", "items": [ { "pagination": 1, "sequence": 0, "title": "【大大寬頻】光纖就是快！愛情好光鮮_ 2.視訊篇", "type": "Full", "sourceType": "1001", "source_type": "Youtube", "typeName": "Youtube", "poster_art_url": "https://i.ytimg.com/vi/FhQ2L1tAIEw/hqdefault.jpg", "description": "【大大寬頻】光纖就是快！愛情好光鮮_ 2.視訊篇\n", "videoId": "FhQ2L1tAIEw", "playListId": null, "url": "FhQ2L1tAIEw" } ] }, { "page": "2", "type": "Full", "items": [ { "pagination": 2, "sequence": 0, "title": "HBO GO", "type": "Full", "sourceType": "1007", "source_type": "QRcode", "typeName": "QRcode", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//uploads/icon/1723769886888.jpg", "description": "HBO GO最新強檔！\n8/16起瘋狂麥斯電影系列之《芙莉歐莎：瘋狂麥斯傳奇篇章》立即線上觀賞！", "url": "https://mwps.tbc.net.tw/product/ott/{STB_SC_ID}/{STB_CA_SN}/{BAT_ID}/hbogo" } ] }, { "page": "3", "type": "Full", "items": [ { "pagination": 3, "sequence": 0, "title": "LiTV隨選影片", "type": "Full", "sourceType": "1007", "source_type": "QRcode", "typeName": "QRcode", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//uploads/icon/1723167782395.png", "description": "LiTV隨選影片年約超值優惠只要$490", "url": "https://mwps.tbc.net.tw/product/ott/{STB_SC_ID}/{STB_CA_SN}/{BAT_ID}/litv" } ] }, { "page": "4", "type": "Horizontal", "items": [ { "pagination": 4, "sequence": 0, "title": "大法師-信徒", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2005/pt%E5%A4%A7%E6%B3%95%E5%B8%AB-%E4%BF%A1%E5%BE%92.png", "description": "當一個12歲的女孩被一個神秘的惡魔附身時，她的父親拼命求助，最終找到了一個人幫忙，此人在1970年代也幫助了自己的女兒從類似的附身事件中倖存", "start_time": "2024/08/17 21:00", "service_id": "2005", "end_time": "2024/08/17 22:50", "channel_num": "65", "channel_name": "HBO HD" }, { "pagination": 4, "sequence": 1, "title": "尚氣與十環傳奇", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch3006/pt%E5%B0%9A%E6%B0%A3%E8%88%87%E5%8D%81%E7%92%B0%E5%82%B3%E5%A5%87.png", "description": "敘述尚氣（劉思慕飾演）自幼接受父親文武（梁朝偉飾演）的鐵血戰鬥培訓，精通各種武術招式。長大後為了逃離家鄉，他改名換姓展開新生活，認識了摯友凱蒂（奧卡菲娜飾演），平靜的日子就這樣過了十年，直到過去再度找上門…", "start_time": "2024/08/16 21:00", "service_id": "3006", "end_time": "2024/08/16 23:50", "channel_num": "66", "channel_name": "東森洋片台 HD" } ] }, { "page": "5", "type": "Horizontal", "items": [ { "pagination": 5, "sequence": 0, "title": "惡女", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2087/pt%E6%83%A1%E5%A5%B3.png", "description": "主播黃立美愛情事業兩得意，工作表現優異獲得晉升，同步籌辦與牙醫大為的婚禮，即將踏入禮堂迎來美好人生。某日，立美的父親忽然表示希望再婚，對象秀蘭其貌不揚、學歷不高卻以擅長烹飪及溫柔的照護緊抓住父親的心。立美的母親在她幼時早逝，多年來與父親相依關係緊密，面對父親突然的婚訊，她以女人的直覺判斷秀蘭肯定不單純。", "start_time": "2024/08/17 21:00", "service_id": "2087", "end_time": "2024/08/17 23:25", "channel_num": "61", "channel_name": "CATCHPLAY電影台 HD" }, { "pagination": 5, "sequence": 1, "title": "雉岳山怪談", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch3005/pt%E9%9B%89%E5%B2%B3%E5%B1%B1%E6%80%AA%E8%AB%87.png", "description": "登山自行車社團「登山吧」的隊長民俊（尹筠相）和隊員們前往他的表妹賢智（金叡園）父親的森林小屋，計畫在山中練車和拍攝影片。深夜時，突然一陣紅光朝他們來襲來，賢智竟被一股奇怪的引力帶走，失去蹤影。民俊急忙到森林中尋人，其他隊員也陸續碰到奇怪的事件…", "start_time": "2024/08/18 21:00", "service_id": "3005", "end_time": "2024/08/18 22:50", "channel_num": "63", "channel_name": "緯來電影台 HD" } ] }, { "page": "6", "type": "Horizontal", "items": [ { "pagination": 6, "sequence": 0, "title": "金牌間諜", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2088/pt%E9%87%91%E7%89%8C%E9%96%93%E8%AB%9C.png", "description": "艾力克斯（歐文威爾森 飾）是位笨手笨腳的中央情報局探員，雖然熱愛間諜的工作，卻常常把任務搞砸。上司交給他的最新任務，是偵破一樁國際軍火走私案，由於這名軍火商熱愛拳擊運動，CIA便藉助金牌拳王凱利（艾迪墨菲 飾）的幫助接近軍火商。而在辦案的過程，由於兩人個性和辦事風格截然不同，引發許多笑料。", "start_time": "2024/08/17 21:00", "service_id": "2088", "end_time": "2024/08/17 23:05", "channel_num": "69", "channel_name": "amc電影台 HD" }, { "pagination": 6, "sequence": 1, "title": "歡樂好聲音2", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch3006/pt%E6%AD%A1%E6%A8%82%E5%A5%BD%E8%81%B2%E9%9F%B32.png", "description": "野心勃勃的無尾熊巴斯特（金獎影帝馬修麥康納 配音）以及他旗下的藝人將他的新穆恩劇院，轉變成當地最火紅的表演場地，但是他現在有一個更大的野心，那就是在光芒萬丈的紅灘市的克里斯托塔劇院，舉辦一場全新歌舞大秀的首演會。", "start_time": "2024/08/22 19:00", "service_id": "3006", "end_time": "2024/08/22 21:20", "channel_num": "66", "channel_name": "東森洋片台 HD" } ] }, { "page": "7", "type": "Horizontal", "items": [ { "pagination": 7, "sequence": 0, "title": "驚弒新娘", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2088/pt%E9%A9%9A%E5%BC%92%E6%96%B0%E5%A8%98.png", "description": "葛瑞絲和卡洛斯一見鍾情，並隨即決定共結連理，幾乎所有卡洛斯的家人都因這項喜訊欣喜若狂，除了相當保護卡洛斯的姊姊潔絲敏，她認為僅僅認識一個月的他們操之過急，並對葛瑞絲心生疑慮。即使葛瑞絲想盡辦法試圖取得潔絲敏的信任，潔絲敏仍察覺葛瑞絲隱藏不可告人的祕密。", "start_time": "2024/08/18 21:00", "service_id": "2088", "end_time": "2024/08/18 22:50", "channel_num": "69", "channel_name": "amc電影台 HD" }, { "pagination": 7, "sequence": 1, "title": "Q18量子預言:1", "type": "Horizontal", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2501/ptQ18%E9%87%8F%E5%AD%90%E9%A0%90%E8%A8%80%3A1.png", "description": "公司為了提供人類最美好的生活製造各種量子產品,而當​科技和人性的相互拉扯，究竟會發生什麼意想不到的事情？", "start_time": "2024/08/16 22:00", "service_id": "2501", "end_time": "2024/08/16 23:00", "channel_num": "30", "channel_name": "三立都會台HD" } ] }, { "page": "8", "type": "Vertical", "items": [ { "pagination": 8, "sequence": 0, "title": "嗨！營業中第4季:1", "type": "Vertical", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch3503/pt%E5%97%A8%EF%BC%81%E7%87%9F%E6%A5%AD%E4%B8%AD%E7%AC%AC4%E5%AD%A3%3A1.png", "description": "《嗨！營業中》第4季由姚元浩、郭泓志、吳映潔、莎莎與乱彈阿翔，挑戰移動營業升級版，上山下海到處烹調美味餐點給各式各樣的客人享用，他們如何同心協力度過難關是一大看點。", "start_time": "2024/08/18 20:00", "service_id": "3503", "end_time": "2024/08/18 22:00", "channel_num": "28", "channel_name": "八大綜合台 HD" }, { "pagination": 8, "sequence": 1, "title": "完美的結婚公式:1", "type": "Vertical", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2508/pt%E5%AE%8C%E7%BE%8E%E7%9A%84%E7%B5%90%E5%A9%9A%E5%85%AC%E5%BC%8F%3A1.png", "description": "為了報復丈夫和家人而選擇契約婚姻的女人，和為了迎娶她作為妻子而假裝契約婚姻的男子之間，驚險又隱秘的「回歸復仇羅曼史」...", "start_time": "2024/08/19 21:00", "service_id": "2508", "end_time": "2024/08/19 22:00", "channel_num": "40", "channel_name": "東森戲劇台 HD" }, { "pagination": 8, "sequence": 2, "title": "KM Special 韓國文化探究竟:1", "type": "Vertical", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2034/ptKM%20Special%20%E9%9F%93%E5%9C%8B%E6%96%87%E5%8C%96%E6%8E%A2%E7%A9%B6%E7%AB%9F%3A1.png", "description": "2024年8月18日 每週日 晚間6點（首播）、每週二 晚間6點（重播）博大精深的韓國，不僅有大家熟悉的韓劇、K-pop和美妝……等，淵遠流長的傳統文化也同樣精彩有趣。一起透過《KM Special 韓國文化探究竟》認識韓國的傳統節日、遊戲、歌舞和美食，享受韓國的千年之美吧！", "start_time": "2024/08/18 18:00", "service_id": "2034", "end_time": "2024/08/18 18:30", "channel_num": "217", "channel_name": "韓國娛樂台KMTV HD" } ] }, { "page": "9", "type": "Full", "items": [ { "pagination": 9, "sequence": 0, "title": "離開美國結婚去第5季:1", "type": "Full", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch2006/pt%E9%9B%A2%E9%96%8B%E7%BE%8E%E5%9C%8B%E7%B5%90%E5%A9%9A%E5%8E%BB%E7%AC%AC5%E5%AD%A3%3A1.png", "description": "離開美國結婚去第5季:遠道而來-對那些以愛之名移居海外的美國人，搬離美國的生活舒適圈值得嗎？還是他們會捧著心碎搬回美國？", "start_time": "2024/08/16 21:00", "service_id": "2006", "end_time": "2024/08/16 23:00", "channel_num": "21", "channel_name": "TLC 旅遊生活 HD" } ] }, { "page": "10", "type": "Full", "items": [ { "pagination": 10, "sequence": 0, "title": "金礦的賭注急流篇第7季:1", "type": "Full", "sourceType": "1008", "source_type": "Program", "typeName": "Program", "poster_art_url": "https://epgstore.tbc.net.tw/acs-api//program/ch4501/pt%E9%87%91%E7%A4%A6%E7%9A%84%E8%B3%AD%E6%B3%A8%E6%80%A5%E6%B5%81%E7%AF%87%E7%AC%AC7%E5%AD%A3%3A1.png", "description": "金礦的賭注急流篇第7季:悲劇的開始 經歷了上一季的挫敗之後，達斯汀赫特帶著一組人馬重回金塊溪。", "start_time": "2024/08/17 21:00", "service_id": "4501", "end_time": "2024/08/17 22:00", "channel_num": "19", "channel_name": "Discovery HD" } ] } ] } | 廣告 | "com.vasott.acsclient.intent.action.RECOMMEND_PROGRAM"
|  | week_highlight | "com.prime.dmg.launcher" | "com.prime.acsclient.update.week_highlight" | { "recommends": [ { "sequence": 1, "title": "【大大寬頻】光纖就是快！愛情好光鮮_ 2.視訊篇", "start_time": null, "end_time": null, "video_id": "FhQ2L1tAIEw", "playlist_id": null, "icon": "https://i.ytimg.com/vi/FhQ2L1tAIEw/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "FhQ2L1tAIEw", "triggers": [] }, { "sequence": 2, "title": "CH18 BBC Earth 舞動西西里", "start_time": null, "end_time": null, "video_id": "aUOpnYxPmtM", "playlist_id": null, "icon": "https://i.ytimg.com/vi/aUOpnYxPmtM/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "aUOpnYxPmtM", "triggers": [] }, { "sequence": 3, "title": "CH23 小尼克頻道 最新熱門節目推薦 ", "start_time": null, "end_time": null, "video_id": "2uDD8ZRHHaA", "playlist_id": null, "icon": "https://i.ytimg.com/vi/2uDD8ZRHHaA/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "2uDD8ZRHHaA", "triggers": [] }, { "sequence": 4, "title": "CH67 AXN 蜘蛛人：返校日", "start_time": null, "end_time": null, "video_id": "bkBgZbZ67jI", "playlist_id": null, "icon": "https://i.ytimg.com/vi/bkBgZbZ67jI/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "bkBgZbZ67jI", "triggers": [] }, { "sequence": 5, "title": "CH65 HBO 乘客", "start_time": null, "end_time": null, "video_id": "jCLYIGYbkrI", "playlist_id": null, "icon": "https://i.ytimg.com/vi/jCLYIGYbkrI/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "jCLYIGYbkrI", "triggers": [] }, { "sequence": 6, "title": "CH61 CATCHPLAY電影台 全境炸裂", "start_time": null, "end_time": null, "video_id": "-xDMReEA1Qc", "playlist_id": null, "icon": "https://i.ytimg.com/vi/-xDMReEA1Qc/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "-xDMReEA1Qc", "triggers": [] }, { "sequence": 7, "title": "CH253 CBeebies 蔬果達人秀", "start_time": null, "end_time": null, "video_id": "XU9bwhTh-x4", "playlist_id": null, "icon": "https://i.ytimg.com/vi/XU9bwhTh-x4/hqdefault.jpg", "app_name": "Youtube", "type": "1001", "videoId": "XU9bwhTh-x4", "triggers": [] } ] } | 本周強檔 | "com.vasott.acsclient.intent.action.RECOMMEND_VOD"
|  | rank_list | "com.prime.dmg.launcher" | "com.prime.acsclient.update.rank_list" | [ { "ranking": 1, "id": 432513, "channel_id": 100064, "service_id": 3001, "channel_name": "TVBS 新聞台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch3001.png", "event_id": "005507091500", "tv_name": "新聞夜視界", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "1.12", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 208714, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 2, "id": 432515, "channel_id": 100009, "service_id": 3003, "channel_name": "東森財經新聞台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch3003.png", "event_id": "005707091600", "tv_name": "銅板美食呷透透:31", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.79", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 146754, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 3, "id": 432517, "channel_id": 100138, "service_id": 3000, "channel_name": "三立新聞台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch3000.png", "event_id": "005407091600", "tv_name": "新聞夜現場", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.7", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 129878, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 4, "id": 432519, "channel_id": 100007, "service_id": 4506, "channel_name": "衛視電影台", "channel_poster": null, "event_id": "006107091540", "tv_name": "九龍不敗", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.55", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 102649, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 5, "id": 432521, "channel_id": 100161, "service_id": 3016, "channel_name": "東森電影台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch3016.png", "event_id": "006207091530", "tv_name": "錢力遊戲", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.53", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 98454, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 6, "id": 432523, "channel_id": 100036, "service_id": 2512, "channel_name": "壹電視新聞台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch2512.png", "event_id": "004907091600", "tv_name": "整點新聞", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.49", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 91520, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 7, "id": 432525, "channel_id": 100171, "service_id": 3017, "channel_name": "LS Time電影台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch3017.png", "event_id": "006407091555", "tv_name": "廟街十二少", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.46", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 86320, "lastUpdatedUTC": "2023-07-10 01:07:21" }, { "ranking": 8, "id": 432527, "channel_id": 100153, "service_id": 2515, "channel_name": "東森新聞台", "channel_poster": "https://epgstore.tbc.net.tw/acs-api//channel/ch2515.png", "event_id": "005107091600", "tv_name": "東森夜線新聞", "start_date": "2023-07-10", "end_date": "2023-07-10", "start_time": "", "end_time": "", "rating": "0.43", "keepRecord": 0, "lastUpdated": "2023-07-09T17:07:21.000Z", "box_count": null, "description": null, "Time_Interval": "00:00-01:00", "TotalSec": 80279, "lastUpdatedUTC": "2023-07-10 01:07:21" } ] | 排行榜 | "com.vasott.acsclient.intent.action.RANKINGLIST"
| 資料來源 | broadcast package name | broadcast action | broadcast intent key | broadcast intent type/value | 說明
| fwinfo | "com.prime.otaupdater" | "com.prime.acsclient.update.ota_param" | is_force_update | boolean / true or false | 是否強制升級
|  |  |  | download_url | String | 升級檔下載網址
|  |  |  | md5_checksum | String | 升級檔MD5
|  |  |  | file_size | int | 升級檔SIZE
|  |  |  | ota_version | String | 升級檔後版本號
|  |  |  | release_notes | String | 發布說明
|  |  |  | model_check_name | String | 比對的model_name
| appinfo | "com.prime.appDownloadManager" | "pesi.broadcast.action.device.manager" | "INSTRUCTION_ID" | 201 | 安裝
|  |  |  | "INSTALL_PKGNAME" | Arraylist<String> / string | 安裝的pacakge name
|  |  |  | "INSTALL_PKG_DOWNLOAD_PATH" | Arraylist<String> / string | apk下載位置
|  |  |  | "INSTRUCTION_ID" | 202 | 移除
|  |  |  | "UNINSTALL_PKGNAME" | Arraylist<String> / string | 移除的package name

## http doc和實際data欄位比較
處理完成 | 類別 | doc內欄位 | 實際data欄位 | prime變數名 | 實際data
V | provision response | sub_client_id | sub_client_id | mqtt_client_id | "5CFB3A8C282E"
Deprecated |  | sub_username | sub_username | mqtt_user_name | "5CFB3A8C282E"
V |  | sub_host | sub_host | mqtt_server_ip | "123.241.239.91"
V |  | sub_port | sub_port | mqtt_server_port | 1883
V |  | sub_tls_port | sub_tls_port | mqtt_tls_server_port | 1883
V |  | sub_qos | sub_qos | mqtt_qos | 2
V |  | sub_topics | sub_topics | mqtt_subscribe_topics | "/config/5CFB3A8C282E"
V |  | pub_topics | pub_topics | mqtt_publish_topics | "/config/status-report/API-0.TBC.NET.TW/2"
V |  | ota_sync_api | ota_sync_api | http_fwinfo_url | "https://acs-portal.tbcnet.net.tw/fwinfo"
V |  | app_sync_api | app_sync_api | http_appinfo_url | "https://acs-portal.tbcnet.net.tw/appinfo"
V |  | launcher_sync_api | launcher_sync_api | http_launchernfo_url | "https://acs-portal.tbcnet.net.tw/launcherinfo"
Deprecated |  | ota_sync_interval | ota_sync_interval | ota_check_interval | 14400
V |  | sw_sync_interval | sw_sync_interval | fwinfo_check_interval | 14400
V |  | Fw_daily_confirm | Fw_daily_confirm | fwinfo_check_daily_interval | 86400
V |  | Sw_group_name | Sw_group_name | mqtt_ota_topic_group_name | "Default"
V |  | App_sync_interval | App_sync_interval | appinfo_check_interval | 3600
V |  | App_daily_confirm | App_daily_confirm | appinfo_check_daily_interval | 86400
Deprecated |  | Launcher_sync_interval | Launcher_sync_interval | launcherinfo_check_interval | 14400
V |  | Launcher_daily_confirm | Launcher_daily_confirm | launcherinfo_check_daily_interval | 86400
V |  | logSize | logSize | save_log_size_mb | "100" | 開機需要先用logcat -G設定大小?
V |  | enable_log | enable_log | is_save_log_enable | FALSE | LOGCAT需要priv-app，不然只能抓到自己APK的
Deprecated |  | HDMIOutControl | HDMIOutControl | hdmi_output_control | "on"
V |  | Launcher_profile | Launcher_profile | launcher_profile_lsit | [] | 需要在ACS頁面將設備套用profile設定, 資料才不為空 "launcher_profile": [ { "appName": "Prime Video(5.7.13+v14.0.0.397-armv7a)", "packageName": "com.amazon.amazonvideo.livingroom", "thumbnail": "https://acs-ota.tbcnet.net.tw/app_bd201/ico/1659963445442.png", //後台的App圖示, App尚未安裝前必須使用它來做排版 "iconPriority": 0, //圖示顯示 0 跟隨App, 1使用後台提供優先 "activityName": null, //若App有指定的開啟方式, 可以從後台指定 "productId": "", //RCU ID本來用來判斷不同遙控器時, 該圖示是否顯示, TBC未使用 "packageParams": {}, //若App有指定的開啟方式, 可以從後台帶參數 "description": "", //手動下載頁面的描述 "fullText": "", //手動下載頁面的完整說明 "appPath": "", //手動下載位置, 倘若沒有上架GooglePlay無法導去商城下載的話 "appVersionCode": "505007013", // 手動下載的版本 "apkLabel": "Prime Video", //手動下載的標籤 "screenCaptures": [], //手動下載的截圖 "displayPosition": 1, //棄用, 可以不參考, 目前t.GW Launcher沒分 "forceUpdate": false //手動下載path不為空時, 是否強制用戶更新才給使用 } ]
△ |  | report_api | report_api | log_upload_url | "https://acs-portal.tbcnet.net.tw/device/setinfo" | 上傳時機 和 成功與否 需確認
Deprecated |  | ad | ad | ad_profile_lsit | [{"url":"https://acs-portal.tbcnet.net.tw/AD"}]
Deprecated |  | notify_center_api | notify_center_api | notify_center_api | "https://acs-portal.tbcnet.net.tw/bandott/messages"
Deprecated |  | DeviceSwitchs | DeviceSwitchs | DeviceSwitchs | {"RMSStatus":0, "TVMAILStatus":1, "HdmiOutStatus":1, "DVRStatus":0, "StandbyRedirectStatus":1, "DTVStatus":1, "IPWhitelistStatus":0, "ForceScreenStatus":0, "LauncherLockStatus":0, "TickerStatus":1, "SystemAlertStatus":0}
V |  | deviceParams | deviceParams | DeviceParams | {"bat_id":"0", "box_si_nit":"12", "network_sync_time":"360"}
△ |  | DeviceOperation | DeviceOperation | DeviceSettings | {"RMSStatus":0, "TVMAILStatus":1, "HdmiOutStatus":1, "DVRStatus":0, "StandbyRedirectStatus":1, "DTVStatus":1, "IPWhitelistStatus":0, "ForceScreenStatus":0, "LauncherLockStatus":0, "TickerStatus":1, "SystemAlertStatus":0, "bat_id":"0", "box_si_nit":"12", "network_sync_time":"360"}
V |  | projectName | projectName | project_name | "TBC"
V |  | projectId | projectId | project_id | 1
△ |  | networkSwitch | networkSwitch | is_network_eth_wifi_auto_switch_enable | 1 | eth_wifi_auto_switch要實作
V |  | topicInfo | topicInfo | mqtt_topic_info | [] | 設備要加入群組,有群組ID． 若ACS有將此設備加入群組, topicInfo就會有值, 內容就是MQTT需要Subscribe的Topic, 因為會根據群組給予不同的MQTT Topic ID
V |  | ConditionTopic | ConditionTopic | mqtt_tv_mail_topic | ["/home/condition/TBC-----"]
V |  | app_group_name | app_group_name | mqtt_app_topic_group_name | "Default"
V |  | Eula | Eula | eula_list | [{"name":"t.Gateway服務條款", "sort":1, "url":"https://www.tbc.net.tw/terms/tgatewaymemberservices", "version":"1.0.0"}]
V |  | music_category | music_category | music_category_list | [ {"name":"華語音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330858497.png", "sort":1, "servicelists":["1534", "1535", "1536", "1543"]}, {"name":"西洋音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330890167.png", "sort":2, "servicelists":["1514", "1515", "1516", "1517", "1518", "1519", "1521"]}, {"name":"東洋音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330824653.png", "sort":3, "servicelists":["1525", "1526", "1527"]}, {"name":"沙發音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330938131.png", "sort":4, "servicelists":["1522", "1523", "1524", "1528", "1531", "1532"]}, {"name":"古典音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586330777070.png", "sort":5, "servicelists":["1529", "1530", "1537"]}, {"name":"其他音樂", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586331013427.png", "sort":6, "servicelists":["1520", "1533", "1538", "1539", "1540", "1541", "1542"]}]
V |  | IllegalNetwork | IllegalNetwork | is_illegal_network | 0
Deprecated |  | storage_server | storage_server | storage_server | "https://epgstore.tbc.net.tw/acs-api/"
V |  | networkQualityDefined | networkQualityDefined | network_quality_info_lsit | [ {"name":"EXCELLENT", "description":"優", "highest":1000, "lowest":30, "id":1}, {"name":"GOOD", "description":"好", "highest":30, "lowest":10, "id":2}, {"name":"MODERATE", "description":"普通", "highest":10, "lowest":1, "id":3}, {"name":"POOR", "description":"差", "highest":1, "lowest":0, "id":4}]
|  | DVRPairHDs | DVRPairHDs | dvr_pair_hdd_info | [] | 盒子從ACS開啟DVR功能, 配對上HDD以後即會與ACS同步HDD資訊 資訊有四個欄位, 都是ACS顯示用, 其中機上盒會拿HDD SN來判斷該硬碟是否綁定 "product_name" : HDD名稱 "serial_number" : HDD SN "label" : 使用者命名標籤 "size" : HDD大小
Deprecated |  |  | dlna | dlna | FALSE
Deprecated |  |  | miracast | miracast | FALSE
Deprecated |  |  | auto_log | auto_log | FALSE
Deprecated |  |  | BplusTrigger | bplus_trigger | "off"
Deprecated |  |  | report_interval | report_interval | 14400
Deprecated |  |  | message_type | message_type | "config"
Deprecated |  |  | group_config_version | group_config_version | "20191008203911"
Deprecated |  |  | uba_white_list | uba_white_list | ""
Deprecated |  |  | UBARecommendation | uba_recommendation | TRUE
Deprecated |  |  | UBARemoteButton | uba_remote_button | TRUE
Deprecated |  |  | UBALaunchPoint | uba_launch_point | TRUE
Deprecated |  |  | UBADirectionKey | uba_direction_key | TRUE
Deprecated |  |  | UBACollect | uba_collect | TRUE
Deprecated |  |  | ubaUploadMin | uba_upload_min | null
Deprecated |  |  | ubaForceUploadHour | uba_force_uplaoder_hour | null
Deprecated |  |  | prompts | prompts | []
Deprecated |  |  | EulaUrl | eula_url | "https://www.tbc.net.tw/terms/tgatewaymemberservices"
Deprecated |  |  | EulaVersion | eula_version | "1.0.0"
△ | provision response | RMSStatus | RMSStatus | is_rms_upload | 0 | rms_upload_data要實作
V | DeviceOperation | TVMAILStatus | TVMAILStatus | is_show_tvmail | 1
△ |  | HdmiOutStatus | HdmiOutStatus | is_hdmi_output | 1 | hdmi_output_control要實作 HdmiOutStatus的數值為1/0, 若數值為0, 只關閉hdmi的輸出, 機上盒仍會是power on
V |  | DVRStatus | DVRStatus | is_dvr_enable | 0
V |  | StandbyRedirectStatus | StandbyRedirectStatus | is_standby_redirect | 1
V |  | IPWhitelistStatus | IPWhitelistStatus | is_ip_whitelist_enable | 0
V |  | ForceScreenStatus | ForceScreenStatus | is_force_lock_screen | 0
V |  | TickerStatus | TickerStatus | is_marquee_display | 1
V |  | SystemAlertStatus | SystemAlertStatus | is_system_alert | 0
V |  | bat_id | bat_id | bat_id | "0" | bat_id跟M/W有關, 機上盒需要此參數來決定顯示頻道 通常RF可以抓到nit資訊, 以TBC為例, 群健與信和的NIT不同;
V |  | box_si_nit | box_si_nit | nit_params | "12" | box_si_nit是TBC MIS帶入ACS的參數, 下發給盒子, 用來比對用戶是否有把盒子移區使用的狀況
V |  | network_sync_time | network_sync_time | network_sync_time | "360"
V |  | home_id |  | home_id
V |  | pin_code |  | pin_code
V |  | member_id |  | member_id
△ |  | pa_day |  | pa_day |  | check_pa_day需要實作
V |  | nit_id |  | nit_id
△ |  | mobile |  | mobile |  | 不知道用途
V |  | zipcode |  | region_code
V |  | so |  | operator_code
Deprecated |  |  | DTVStatus | dtv_status | 1
Deprecated |  |  | LauncherLockStatus | is_launcher_lock | 0
V | provision response | name | name | eng_description | EXCELLENT | GOOD | MODERATE | POOR
V | networkQualityDefined | description | description | chinese_description | 優 | 好 | 普通 | 差
V |  | highest | highest | highest_speed | 1000 | 30 | 10 | 1
V |  | lowest | lowest | lowest_speed | 30 | 10 | 1 | 0
V |  | id | id | index | 1 | 2 | 3 | 4
V | provision response | appName |  | app_name |  | 整串送給launcher處理
V | launcher_profile | packageName |  | package_name
V |  | thumbnail |  | thumbnail_url |  | //後台的App圖示, App尚未安裝前必須使用它來做排版
V |  | iconPriority |  | icon_priority |  | //圖示顯示 0 跟隨App, 1使用後台提供優先
V |  | activityName |  | launch_activity_name |  | //若App有指定的開啟方式, 可以從後台指定
V |  | productId |  | rcu_id |  | //RCU ID本來用來判斷不同遙控器時, 該圖示是否顯示, TBC未使用
V |  | packageParams |  | lunch_app_params |  | //若App有指定的開啟方式, 可以從後台帶參數
V |  | description |  | app_short_description |  | //手動下載頁面的描述
V |  | fullText |  | app_full_description |  | //手動下載頁面的完整說明
V |  | appPath |  | app_download_url |  | //手動下載位置, 倘若沒有上架GooglePlay無法導去商城下載的話
V |  | appVersionCode |  | app_version_code |  | // 手動下載的版本
V |  | apkLabel |  | app_dispaly_label |  | //手動下載的標籤
V |  | screenCaptures |  | app_screen_captures |  | //手動下載的截圖
V |  | displayPosition |  | app_disaply_position |  | //棄用, 可以不參考, 目前t.GW Launcher沒分
V |  | forceUpdate |  | is_force_update |  | //手動下載path不為空時, 是否強制用戶更新才給使用
V | fwinfo | driven_by | driven_by |  | "user" | system mode 可以在下載完更新檔後 a. 立即更新 b.在待機狀態時更新c 在下次重開機後更新 d.在指定時間段更新(e. 01:00~05:00) user mode 會跳出通知提醒用戶主動更新
V |  | fw_version | fw_version |  | "" | 給ota app處理
V |  | release_notes | release_notes |  | "" | 給ota app處理
V |  | fw_path | fw_path |  | {"low_bw_url":"", "high_bw_url":""} | 給ota app處理 | 目前高低速網址相同
V |  | low_bw_url | low_bw_url |  | "" | 給ota app處理
V |  | high_bw_url | high_bw_url |  | "" | 給ota app處理
V |  | md5_checksum | md5_checksum |  | "" | 給ota app處理
V |  | file_size | file_size |  | 0 | 給ota app處理
|  | status |  |  |  | 1. 會缺少欄位, 並且多半為空字串, 是因為Server端尚未設定有效的OTA更新任務(例如: OTA版本要高於Box目前版本才算有效) 2. Server端OTA設定的模式不同, 提供的欄位也會不一樣, 請參考API文件 p15. fwinfo欄位說明, 例如: 更新模式設定為 user時, otaAfterxxx的參數就不會出現 3. 取得方式, 請使用PostMan模擬POST即可, 可參考API文件 p13. , ps. 設定一個Box連上Server後, 再使用PostMan模擬該Box發送POST request, 若Box不在連線狀態, Server可能會擋掉一些request
V |  | sw_sync_interval
V |  | fw_daily_confirm
V |  | model_checker |  |  |  | 給ota app處理
V |  | sw_group_name
V |  | otaAfterStandby |  |  |  | 只有設置為系統更新為driven_by==system的狀況下才會有 otaAfterStandby otaAfterBoot otaAfterImmediately otaAfterTime
V |  | otaAfterBoot
V |  | otaAfterImmediately
V |  | otaAfterTime
V | appinfo | app_path | app_path |  | "https://acs-ota.tbcnet.net.tw/app_bd201" | 下載路徑= app_path+"/"+apk_name;
V |  | app_group_name | app_group_name |  | "Default"
V |  | sw_sync_interval | sw_sync_interval |  | 14400
V |  | app_sync_interval | app_sync_interval |  | 3600
V |  | apps_info | apps_info |  | [] | 需要將該設備從ACS設定好對應的應用程式安裝Profile才會有內容
V |  | package_name |  |  |  | //App的PackageName
V |  | apk_name |  |  |  | //App檔案名稱,用來組合下載連結
V |  | md5_checksum |  |  |  | //Size checksun
V |  | version_code |  |  |  | //四欄為APK的資訊
V |  | version_name
V |  | sdk_version
V |  | target_version
V |  | enabled |  |  |  | //0: uninstall 1: install
V |  | mode |  |  |  | //自動安裝或手動安裝
V | launcherinfo | otaSyncInterval | otaSyncInterval |  | 14400
Deprecated |  | hdmiOutControl | hdmiOutControl |  | "on"
V |  | projectName | projectName |  | "TBC"
V |  | modelName | modelName |  | "TATV-8000" | 無功能
V |  | androidVersion | androidVersion |  | "9" | 無功能
V |  | otaStarted | otaStarted |  | "2017-01-11 00:00:00" | 無功能
Deprecated |  | otaDrivenBy | otaDrivenBy |  | "user"
V |  | otaAfterStandby | otaAfterStandby |  | 0
V |  | otaAfterBoot | otaAfterBoot |  | 0
V |  | otaAfterImmediately | otaAfterImmediately |  | 0
V |  | otaAfterTime | otaAfterTime |  | null
V |  | appProfileId | appProfileId |  | 0 | 無功能，這幾個ID對應到後台建立的Profile ID, 但後來Client side其實對這些ID並沒有使用用途
V |  | recommendationProfileId | recommendationProfileId |  | 0 | 無功能，這幾個ID對應到後台建立的Profile ID, 但後來Client side其實對這些ID並沒有使用用途
V |  | hotVideoProfileId | hotVideoProfileId |  | 0 | 無功能，這幾個ID對應到後台建立的Profile ID, 但後來Client side其實對這些ID並沒有使用用途
V |  | networkSwitch | networkSwitch |  | 1
V |  | logSize | logSize |  | "100"
V |  | ledStyle | ledStyle |  | "7Seg" | 無功能
V |  | enable_log | enable_log |  | false
V |  | sw_group_name | sw_group_name |  | "Default"
V |  | sw_sync_interval | sw_sync_interval |  | 14400
V |  | app_group_name | app_group_name |  | "Default"
V |  | app_sync_interval | app_sync_interval |  | 3600
Deprecated |  | launcher_sync_interval | launcher_sync_interval |  | 14400
Deprecated |  | HDMIOutControl | HDMIOutControl |  | "on"
V |  | launcher_profile | launcher_profile |  | []
Deprecated |  |  | btMac |  | null
Deprecated |  |  | dlna |  | false
Deprecated |  |  | miracast |  | false
Deprecated |  |  | reportInterval |  | 3600
Deprecated |  |  | bPlusTrigger |  | "off"
Deprecated |  |  | hdmiOutControlStatus |  | "on"
Deprecated |  |  | hdmiPatch |  | FALSE
Deprecated |  |  | condition1 |  | null
Deprecated |  |  | condition2 |  | null
Deprecated |  |  | condition3 |  | null
Deprecated |  |  | condition4 |  | null
Deprecated |  |  | condition5 |  | null
Deprecated |  |  | otaConfigTime |  | "1721294804060"
Deprecated |  |  | appConfigTime |  | "1721294804060"
Deprecated |  |  | deviceLastFwVersionId |  | null
Deprecated |  |  | videoRecommendationId |  | 0
Deprecated |  |  | scheduleProfileId |  | 0
Deprecated |  |  | ubaUploadMin |  | null
Deprecated |  |  | ubaForceUploadHour |  | null
Deprecated |  |  | report_interval |  | 14400
Deprecated |  |  | auto_log |  | false
Deprecated |  |  | group_config_version |  | "20191008203911"
Deprecated |  |  | UBARecommendation |  | true
Deprecated |  |  | UBARemoteButton |  | true
Deprecated |  |  | UBALaunchPoint |  | true
Deprecated |  |  | UBADirectionKey |  | true
Deprecated |  |  | UBACollect |  | true
Deprecated |  |  | BplusTrigger |  | "off"

## mqtt data
mqtt receive : /config/5CFB3A8C282E message : | mqtt receive : /config/5CFB3A8C282E message
{ "type":"Ota Group Change", "data": { "BplusTrigger":"off", "HDMIOutControl":"on", "UBARecommendation":true, "UBARemoteButton":true, "UBALaunchPoint":true, "UBADirectionKey":true, "UBACollect":true, "fw_daily_confirm":86400, "launcher_daily_confirm":86400, "uba_white_list":"", "enable_log":false, "auto_log":false, "DeviceOperation": { "RMSStatus":0, "TVMAILStatus":1, "HdmiOutStatus":1, "DVRStatus":0, "StandbyRedirectStatus":1, "DTVStatus":1, "IPWhitelistStatus":0, "ForceScreenStatus":0, "LauncherLockStatus":0, "TickerStatus":1, "SystemAlertStatus":0, "bat_id":"0", "box_si_nit":"12", "network_sync_time":"360" }, "storage_server":"https://epgstore.tbc.net.tw/acs-api/" }, "timestamp":"1721708163755" } | { "type":"App Group Change", "data": { "app_path":"", "apps_info":[], "launcher_profile":[], "categoryList":[], "ad_profile":[], "recommends":[ { "title":"MyVideo熱門推薦自動", "start_time":null, "end_time":null, "video_id":null, "playlist_id":"0", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1586480650217.png", "app_name":"myVideo", "type":"1002", "triggers":[ { "activity_name":"CP", "package_params": { "EXTRA_VIDEO_ID":"" }, "trigger_uri":null, "package_name":"com.taiwanmobile.myVideotv", "min_version_code":0, "max_version_code":0, "intent_flags":["0"] }] }, { "title":"friDay影音", "start_time":null, "end_time":null, "video_id":null, "playlist_id":"0", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1585291136394.jpg", "app_name":"friDay影音", "type":"1002", "triggers":[ { "activity_name":"CP", "package_params": { "EXTRA_VIDEO_ID":"" }, "trigger_uri":null, "package_name":"net.fetnet.fetvod.tv", "min_version_code":0, "max_version_code":0, "intent_flags":["0"] }] }, { "title":"LiTV熱門", "start_time":null, "end_time":null, "video_id":null, "playlist_id":"0", "icon":"https://acs-ota.tbcnet.net.tw/app_bd201/ico/1590142706296.png", "app_name":"com.litv.cable.home", "type":"1002", "triggers":[ { "activity_name":"CP", "package_params": { "EXTRA_VIDEO_ID":"" }, "trigger_uri":null, "package_name":"com.litv.cable.home", "min_version_code":0, "max_version_code":0, "intent_flags":["0"] }] }, { "title":"CH43_秘密的男人", "start_time":null, "end_time":null, "video_id":"iwHil_LEtmo", "playlist_id":"https://youtu.be/iwHil_LEtmo", "icon":"https://i.ytimg.com/vi/iwHil_LEtmo/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"iwHil_LEtmo", "triggers":[] }, { "title":"CH65_第三佈局 塵沙惑", "start_time":null, "end_time":null, "video_id":"WZIPfTTcZLw", "playlist_id":null, "icon":"https://i.ytimg.com/vi/WZIPfTTcZLw/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"WZIPfTTcZLw", "triggers":[] }, { "title":"CH62_咒術迴戰", "start_time":null, "end_time":null, "video_id":"sQ02SCe-0Qk", "playlist_id":null, "icon":"https://i.ytimg.com/vi/sQ02SCe-0Qk/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"sQ02SCe-0Qk", "triggers":[] }, { "title":"CH85_派遣女醫-X", "start_time":null, "end_time":null, "video_id":"WMXbHiygbwQ", "playlist_id":null, "icon":"https://i.ytimg.com/vi/WMXbHiygbwQ/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"WMXbHiygbwQ", "triggers":[] }, { "title":"CH21_野性拉丁美洲", "start_time":null, "end_time":null, "video_id":"D_WtP6reDFg", "playlist_id":null, "icon":"https://i.ytimg.com/vi/D_WtP6reDFg/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"D_WtP6reDFg", "triggers":[] }, { "title":"CH21_動物生死鬥", "start_time":null, "end_time":null, "video_id":"fVveINmHxl0", "playlist_id":null, "icon":"https://i.ytimg.com/vi/fVveINmHxl0/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"fVveINmHxl0", "triggers":[] }, { "title":"CH19_富豪谷底求翻身", "start_time":null, "end_time":null, "video_id":"kK4uGh-dg4c", "playlist_id":null, "icon":"https://i.ytimg.com/vi/kK4uGh-dg4c/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"kK4uGh-dg4c", "triggers":[] }, { "title":"CH20_明星變蛋糕", "start_time":null, "end_time":null, "video_id":"y46ONgJWdtw", "playlist_id":null, "icon":"https://i.ytimg.com/vi/y46ONgJWdtw/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":"y46ONgJWdtw", "triggers":[] }, { "title":"CH19_硬派電動車", "start_time":null, "end_time":null, "video_id":null, "playlist_id":null, "icon":"https://i.ytimg.com/vi/u_ePmUCuwZE/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":null, "triggers":[] }, { "title":"CH21_鱷魚拍檔這一家", "start_time":null, "end_time":null, "video_id":null, "playlist_id":null, "icon":"https://i.ytimg.com/vi/gdkpysPcU2c/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":null, "triggers":[] }, { "title":"CH234_南方賽車狂", "start_time":null, "end_time":null, "video_id":null, "playlist_id":null, "icon":"https://i.ytimg.com/vi/g462MqnzAZ4/hqdefault.jpg", "app_name":"Youtube", "type":"1001", "videoId":null, "triggers":[] } } }